**Buffalo County Rooted in Relationships Work Plan: 2017-18**

**Mission:** All Buffalo County children have strong social emotional development.

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Goal: Create public awareness for social emotional development for ages 0-8 in all Buffalo County communities. | | | | |
| Objective 1: Increase the percent of parents with children 0-8 years of age, reporting awareness of early development and social emotional development. *(establish baseline in 2018 with Buffalo County Adult Behavioral Risk Factor Survey)*  Strategy 1.1 Collaborate with and sustain established social emotional education partners in Buffalo County to support early Childhood Development. | | | | |
| Activities | **Outputs** | **Projected Completion** | **Who’s Responsible?** | **Notes** |
| 1.1a Establish an awareness baseline by collecting data | Survey question(s) | January 2018 | Tana Miller |  |
| 1.1b Engage new members through presenting through Community Connections annually. | One Community Connections presentation | June 2018 | Tana Miller |  |
| 1.1c Identify shared outcomes among partners. | # of stakeholders reporting outcomes | June 2018 | RiR Committee |  |
| 1.1d Promote each partners activities under the HealthyMINDS collaborative. | # of Facebook posts  # of Facebook shares | June 2018 | Tana Miller  Maggie Lesiak |  |
| 1.1e Develop a list of current social emotional programs and their outcomes, i.e. COSP, 2nd Step, Parent Psychotherapy, Ages and Stages, School Based Pyramid model. | # of Second Step classrooms  # COSP participants  # of Parent Psychotherapy participants  # of early learning classrooms implementing Pyramid | June 2018 | RiR Committee |  |
| 1.1f Ensure partners’ understand outcomes align with HealthyMINDS logic model. | HealthyMINDS Logic Model | June 2018 | Tana Miller  HealthyMINDS |  |
| 1.1g Identify needs for additional social emotional partners, program or other assets. | # of new partners  # of new assets | June 2018 | RiR Committee |  |
| 1.1h Research pediatricians educational materials provided to parents on social emotional development | List of educational materials | March 2018 | Tana Miller  RiR Committee |  |
| 1.1i Promote social emotional awareness campaign in Buffalo County through social media, radio, billboard and newspaper ads | # of advertisements |  |  |  |
| Strategy 1.2 Develop an ‘All Child Care is High Quality’ awareness campaign. | | | | |
| Activities | **Outputs** | **Projected Completion** | **Who’s Responsible?** | **Notes** |
| 1.2a Develop a guideline of ‘All Child Care is High Quality”. | List of guidelines | January 2018 | Tana Miller  RiR Committee | \*Utilize Step-Up to Quality |
| 1.2b Host parent meetings is 50% of the Buffalo County communities to share and discuss quality child care guidelines. | # of parents in attendance  # of meetings held | June 2018 | Tana Miller  Maggie Lesiak |  |
| 1.2c Engage child care provider and early learning centers to share and discuss community quality child care guidelines | # of child care providers in attendance  # of meetings held | June 2018 | Tana Miller  RiR Committee |  |
| 1.2d. Engage physicians in sharing at least one of the high quality child care guidelines given to parents | # of physicians engaged | June 2018 | Tana Miller  RIR Committee |  |
| Objective 2: Engage 14 Childcare Providers and 6 Center-Based Childcare Directors in Pyramid Model Implementation by June 2018. | | | | |
| Activities | **Outputs** | **Timeline** | **Who’s Responsible?** | **Notes** |
| 2a. Lead Coach to conduct Pyramid Module Trainings and Directors Training | # of trainings  # of participants | -Director Training July 7  -Module 1A: August 12  -Module 1B: October 28  -Module 2A: January 13  -Module 2B: April 7 | Lead Coach, Coaches, Providers, Directors |  |
| 2b. Coaching support to Directors and Providers | # of hours of coaching  # Providers Goals met | June 2018 | Lead Coach, Coaches |  |
| 2c. Lead Coach host and support providers in 9 Provider Collaboration Meetings | # of collaboration meetings  # of participants | June 2018 | Lead Coach, Providers |  |
| 2d. Coaches increase professional development | Coaches attend NTI  # of Reflective Consultation Meetings  # of Internal Coach meetings | April 2018 |  |  |
| 2e. Coaches to track successes and challenges through implementation |  | June 2018 |  |  |